## Web
|  | Red color |  | Critical Severity |  |  | Close Defect
|  | Yellow color |  | High Severity |  |  | Reopen Defect
|  | Orange color |  | Medium Severity |  |  | Not a defect
|  | Green Color |  | Low severity |  |  | Open
DATE | DEFECT_ID | PROJECT NAME | MODULE NAME | SUB-MODULE NAME | SUMMARY | DESCRIPTION | DEFECT TYPE | PHASE | STATUS | SEVERITY | PRIORITY | REPORTED BY | REPORTED ON | ASSIGN TO | Defect Resolved date
2023-12-30 | D_KokanSerach_Login | KokanSerach | Login | SignUp | OTP Window Showing. | Steps: 1.Click On Login
2.Click on Signup
3.Enter Full Name
4.Enter Phone number
5.Enter Mail
6.Enter password
7.Enter confirmed Password
8.Click on Terms & condition
9.Click on Save Button
Expected Result: Without Entered 'Name' fiiled the form and click on Save Button dispalyed error message"Filed is required'
[6 empty] | Actual Result: Without Entered 'Name' Filled th form & click on Save button OTP Window Showing. | Wrong Defect | Testing | Done | Medium |  | neha | 2022-12-30 | Akash | 2023-01-03
2023-12-30 | D_KokanSerach_Login | KokanSerach | Login | SignUp | "Work as Volunteer" Checkbox dispalying Mandatory. | Steps: 1.Click On Login
2.Click on Signup
3.Enter Full Name
8.Click on Terms & condition
9.Click on Save Button
Expected Result: "Work as Volunteer" Checkbox should not be dispalyed as Mandatory
[6 empty] | ActualResult: "Work as Volunteer" Checkbox dispalying Mandatory. | Wrong Defect | Testing | Open | Low |  | neha | 2022-12-30 | Akash | NA
2023-12-30 | D_KokanSerach_Login | KokanSerach | Login | SignUp | "mandatory mark is displaying | Steps: 1.Click on Login
2.Click on Signup
3.Enter Full Name
4.Click on Terms & condition
Expected Result: Mandatory Mark should not be dispalyed at 'Work as volunteer'
[6 empty] | Actual result: "mandatory mark is displaying | Non-functional defect | Testing | Open | Not a Bug |  | neha | 2022-12-30 | akash | NA
2023-12-30 | D_KokanSerach_Login | KokanSerach | Login |  | displaying message"User does not exist". | Steps: 1.Click on Login
2.Enter Mailid
3.Click on Password
4.Click on login button
Expected result: Without Enterd @ and .(dot) in gmail filed and click on submit button dispalyed error message" Please Enter Valid emailid".
[6 empty] | Actual result: After click on submit button displaying message"User does not exist". | Non-functional defect | Testing | Done | Low |  | neha | 2022-12-30 | akash | 2023-01-03
2023-12-31 | D_KokanSerach_Apps_Event | KokanSerach | Add Event |  | Mandatory field mark is not showing | Steps: 1.Click on Apps
2.Click on Add Event
3.Filled Add event form
Expected Result: Mandatory mark (*) should be dispalyed.
[6 empty] | Actual result: Mandatory field mark is not showing. | Missing Defect | Test | Done | Not a bug |  | neha | 2022-12-31 | akash | 2023-01-03
2023-12-31 | D_KokanSerach_Apps_Event | KokanSerach | Add Event |  | "Event name' field is accepting alphanumeric values | Steps: 1.Click On Apps
2.Click on Add Event
3.Enter Event Name
4.Select Start date
5.Select End Date
6.Event Addres
7.Event Description
8.Selcect Img
9.Select Event Free or charges?
10.Click on Save button
Expected Result: "Event Name " field should be accepted Alphabets only.
[6 empty] | Actual Result: "Event name' field is accepting alphanumeric values. | Wrong functional | Test | Open | Medium |  | Neha | 2022-12-31 | Akash | 2023-01-03
2023-12-31 | D_KokanSerach_Apps_Event | KokanSerach | Add Event |  | Previous date also accepting in Select date field. | Steps: 1.Click On Apps
2.Click on Add Event
3.Enter Event Name
4.Select Start date
5.Select End Date
Expected Result: Date should be selected Accoring to start date Should not take a past date in Select event date
[6 empty] | Actual Result: Previous date also accepting in Select date field. | Wrong Functional | Testing | Done | Medium |  | Neha | 2022-12-31 | Akash | 2023-01-03
2023-12-31 | D_KokanSerach_Apps_Event | KokanSerach | Add Event |  | Enter Event Name" Comment is displaying. | Steps: 1.Click On Apps
2.Click on Add Event
3.Enter Event Name
4.Select Start date
5.Select End Date
6.Enter Event Address
Expected Result: Field comment Name should be "Enter Event Address"
[6 empty] | Actual Result: 'Enter Event Name" Comment is displaying. | Non functional | Testing | Done | Not a bug |  | Neha | 2022-12-31 | Akash | 2023-01-03
2023-12-31 | D_KokanSerach_Apps_Event | KokanSerach | Add Event |  | Withouting selecting Image form subbmitting successfully. | Steps: 1.Click on Apps
2.Click on Add Event
3.Enter Event name
4.Select Start date
5.Select End Date
6.Select Event Image
Expected Result: Without Selected Event image click on Submit button dispalyed error note ' please select image.
[6 empty] | Actual result: Withouting selecting Image form subbmitting successfully. | Wrong functional | Testing | Open | Medium |  | Neha | 2022-12-31 | Akash | Image field is not Mandatory
2023-12-31 | D_KokanSerach_Apps_Event | KokanSerach | Add Event |  | Without approval added event is showing on Event calander | Steps: 1.Click on Apps
2.Click on Add Event
3.Enter Event name
4.Select Start date
5.Select End Date
6.Select Event Image
7.Click on save button
Expected Result: Without Event Approval ,added event should not be displayed on event calander.
[6 empty] | Actual result: Without approval added event is showing on Event calander | Wrong functional | Testing | Done | Medium |  | Neha | 2022-12-31 | Akash | 2023-01-03
2023-12-31 | D_KokanSerach_Apps_Event | KokanSerach | Add Event |  | Charges filed is accepting Aphanumerc values. | Steps: 1.Click on Apps
2.Click on Add Event
3.Enter Event name
4.Select Start date
5.Select End Date
6.Select Event Image
7.Click on Paid
8.Enter Charges
Expected Result: 'Event Charges' field should be accepeted only numerical values
[6 empty] | Actual Result; 'Event Charges 'filed is accepting Aphanumerc values. | Wrong functional | Testing | Done | Medium |  | Neha | 2022-12-31 | Akash | 2023-01-03
2023-12-31 | D_KokanSerach_Apps_Event | KokanSerach | Add Event |  | Without Entered chages form submiting successfully. | Steps: 1.Click on Apps
2.Click on Add Event
3.Enter Event name
4.Select Start date
5.Select End Date
7.Click on Paid
8.Enter Charges
Expected Result: Without Entered Charges and click on Save button ,dispalyed error note"Enterd Event Charge".
[6 empty] | Actual Result: Without Entered charges ,and click on save form submited successfully. | Wrong functional | Testing | Done | Medium |  | Neha | 2022-12-31 | Akash | 2023-01-03
2023-12-31 | D_KokanSerach_Apps_Blog | KokanSerach | Add Blog |  | Without Entering Blog Description and click on save button form submited successfully. | Steps: 1.Click on Apps
2.Click on Add Blog
3.Selected Image
4.Selected Category
5.Selected Heading
6.Enter Blog Description 7.Click on Save button
Expected Result: Without entered blog Description Click on Save button,dispalyed error note 'Filled this field.
[6 empty] | Actual Result: Without Entering Blog Description and click on save button form submited successfully. | Wrong functional | Testing | Done | Medium |  | Neha | 2022-12-31 | Akash | 2023-01-03
2023-01-02 | D_KokanSerach_Apps_Blog | KokanSerach | Blog | Edit Blog | select 1st option and click on 'Submit' button it dispalying "Value error". | Steps: 1.Click on blog
2.Click on edit
3.Select Category
6.Click on Save
Expected Result: 'Selcted category or .. option should not be selcted.
[6 empty] | Actual Result: When select 1st option and click on 'Submit' button it dispalying "Value error". | Wrong functional | Testing | Done | Medium |  | Neha | 2023-01-02 | Akash | 2023-01-03
2023-01-02 | D_KokanSerach_Apps_Blog | KokanSearch | Blog | Add Blog | Content displying gray in colour. | Steps: 1.Click on Blog
2.Select Blog Image
3.Select Category
4.Enter Title
5.Enter Description
6.Click ln Save
Expected Result: Entered "Description 'Content should be dispalyed in BLACK colur.'
[6 empty] | Actual rfesult: Content displying gray in colour. | non functional | Testing | Done | Low |  | Neha | 2023-01-02 | Akash
2023-01-02 | D_KokanSerach_Apps_Blog | KokanSerach | Blog | Edit Blog | dislayed " VAlue error". | Steps: 1.Click on blog
2.Click on edit
3.Select Category
4.Enter Heading
5.Enter Description
6.Click on save button
Expected result: Description field keep blank and click on save button form should not be submitted. Dispalyed error mesage"Filled this field"
[6 empty] | Actual Result: When Description field keep blank & click on save button dislayed " VAlue error". | Wrong functional | Testing | Done | Medium |  | Neha | 2023-01-02 | Akash | 2023-01-03
2023-01-02 | D_KokanSerach_Apps_Blog | KokanSerach | Blog | Edit Blog |  | Steps: 1.Click on Blog
2.Click on share button on card
3.Click on Messanger
Expected result: Page should be redirect to Messager login window.
[6 empty] | Actual Result: Page is redirect to Whatsapp window. | Wrong functional | Testing | Done | Medium |  | Neha | 2023-01-02 | Akash | 2023-01-06
2023-01-02 | D_KokanSerach_Apps_Album | KokanSerach | Album | Add Album | Without entrerd 'Album NAme' form submitted successfully. | Steps: 1.Click on Add Upload Photo
2.Click on Crete Album
3.Select category
4.Select Location
5.Click on Submit button
Expected result: Without Entered Album name Click on Submit button ,it should be displayed error note" Field is required
[6 empty] | Actual Result: Without entrerd 'Album NAme' form submitted successfully. | Wrong functional | Testing | Done | Medium |  | Neha | 2023-01-02 | Akash | 2023-01-06
2023-01-02 | D_KokanSerach_Apps_Album | KokanSerach | Album |  | Without selcting cover imges form submited successfully. | Steps: 1.Click on Add Upload Photo
2.Click on Create Album
3.Select Category
4.Enter Location
5.Click on submit button
Expected Result: Without selcted images click on submit button dispalyed error note"Select image."
[6 empty] | Actual Result: Without selcting cover imges form submited successfully. | Wrong functional | Testing | Done | Medium |  | Neha | 2023-01-02 | Akash | 2023-01-06
2023-01-02 | D_KokanSerach_Apps_Album | KokanSerach | Album |  | Mandatory sign is not dispalying foe Cover image | Steps: 1.Click on Add Upload Photo
2.Click on Create Album
3.Clcik on Select Category
4.select Location
5.Select cover Photo
Expected Result: Manadtory field should be dispalyed (*)
[6 empty] | Actual Result: Mandatory sign is not dispalying foe Cover image | Wrong functional | Testing | Done | Low |  | Neha | 2023-01-02 | Akash
2023-01-04 | D_KokanSerach_Apps_Album | KokanSerach | Album |  | Image is not editable. | Steps: 1.Click on Creat Album
2.Enter album Name
3.select Category
4.Select Loacation
Expected Result: cancel imgae/change image option should dispalyed. Image not editable
[6 empty] | Actual result: If user select any image it does not chnage Image is not editable. | Wrong functional | Testing | Open | Medium |  | Neha | 2023-01-04 | Akash
2023-01-04 | D_KokanSerach_Apps_ | KokanSerach | Apps | List business | Field is accepting less than 6 digit numbers | Steps: 1.Click on List Business
2.Enter Name
3.Enter Address1
4.Enter Address2
5.Select District
6.Select taluka
7.Select Village
8.Enter Pincode
Expeced Result: 'Pincode ' field should be accepted 6 digit number only.
[6 empty] | Actual Result: 'Pincode' field is accepting less than 6 digit number. | Wrong functional | Testing | Done | Low |  | Neha | 2023-01-04 | Akash | 2023-01-06
2023-01-04 | D_KokanSerach_Apps_ | KokanSerach | Apps | List business | Error note is missing | Steps: 1.Click on List Business
2.Enter Name
3.Enter Address1
4.Enter Address2
5.Select District
6.Select taluka
7.Select Village
8.Enter Pincode 9.Click on next
Expeced Result: If field should be accpeted Less than 6 digit numers then dispalyed error note, "Invalid pin code"
[6 empty] | Actual Result: Without showing error note click on next button page is redirect to next page | Missing | Testing | Done | Low |  | Neha | 2023-01-04 | Akash | 2023-01-06
2023-01-04 | D_KokanSerach_Apps_ | KokanSerach | Apps | List business | Less than 10 digit number accepted in Mobile number field. | Steps: 9.Click on next
10.Selcte Business Category
11.select Business Sub Category
12.Enter Business Name
13.Enter Business Description
14.Enter Whatsapp number
Expeced Result: 10 digit numeric values should be accepted in Mobile number
[6 empty] | Actual Result: Less than 10 digit number accepted in Mobile number field. | Wrong Functional | Testing | Done | Medium |  | Neha | 2023-01-04 | Akash | 2023-01-06
2023-01-04 | D_KokanSerach_Apps_ | KokanSerach | Apps | List Business | Error note is missing | Steps: 9.Click on next
10.Selcte Business Category
11.select Business Sub Category
12.Enter Business Name
13.Enter Business Description
14.Enter Whatsapp number
15.Enter Business Image
16.Enter Website
17.Enter Business Address1
18.Enter Business Address2
19.Click on Next
Expetced Result: Dispalyed error note 'Enter 10 digit numbers"
[6 empty] | Actual Result: Without showing error note click on next button page is redirect to next page | Missing Functional | Testing | Done | Medium |  | Neha | 2023-01-04 | Akash | 2023-01-06
2023-01-04 | D_KokanSerach_Apps_ | KokanSerach | Apps | List Business | Error note is missing | Steps: 9.Click on next
10.Selcte Business Category
11.select Business Sub Category
12.Enter Business Name
13.Enter Business Description
14.Enter Whatsapp number
15.Enter Business Image
16.Enter Website
17.Enter Business Address1
18.Enter Business Address2
19.Click on Next
Expected Result: Dispalyed Error note"Select Business Iamge"
[6 empty] | Actual result: Error note is missing | Missing Functional | Testing | Done | Low |  | Neha | 2023-01-04 | Akash | 2023-01-06
2023-01-04 | D_KokanSerach_Apps_ | KokanSerach | List Business | Edit Business | Submit' button is not clickable. | Steps: 1.Click on Business profile
2.Click on Edit business
3.Check User info
4.Click on next
5.Edit Business info
6.check Keyword
7. Clickk on Submit
Expected result: After edit form displayed Message' Business profile update successfully".
[6 empty] | Actual Result: 'Submit' button is not clickable. | Wrong functioanl | Testing | Open | Medium |  | Neha | 2023-01-04 | Akash
2023-01-04 | D_KokanSerach_Home | KokanSerach | Home | Album | Newely added album dispaying at last | Steps: 1.Click on Album on home page
Expected Result: Latest Added album should be dispalyed at 1 st.
[6 empty] | Actual Result: Newely added album dispaying at last | Wrong functioanl | Testing | Done | Low |  | Neha | 2023-01-04 | Akash | 2023-01-06
2023-01-04 | D_KokanSerach_Home | KokanSerach | Home | Album | Images size is not displying properly. | Step: 1.Click on Album onHome Page.
2.Click on any Album
Expected Result: In album Size of the all images should be same
[6 empty] | Actual Result: Images size is not displying properly. | Wrong Functional | Testing | Done | Medium |  | Neha | 2023-01-04 | Akash | 2023-01-06
2023-01-05 | D_kokanSearch_Home | kokanSearch | Home |  | menu is not hilighted. | Steps: 1.Go to Home page
Expected Result: When User click on any option on the Nav bar that menu should be highlighted.
[6 empty] | Actua result: When Click on the option on the nav bar that menu is not hilighted. | Missing Functional | Testing | Done | Medium |  | Neha | 2023-01-05 | Akash | 2023-01-06
2023-01-05 | D_kokanSearch_Home | kokanSearch | Home | Album | Mouse cursor not changes. | Steps: 1.Click on Album on Home PAge
2.Click On Category from side Bar
Expected Result: When Mouse Over On 'Category Option ' coursor should be changed
[6 empty] | Actual result: Mouse cursor not changes. | Wrong Functional | Testing | Done | Low |  | Neha | 2023-01-05 | Akash | 2023-01-06
2023-01-05 | D_kokanSearch_Home | kokanSearch | Home | Tours | key Information Option Is clickable | Steps: 1.Click on Tours
2.Click on any Tours
3.Go to key Information
Expeced Result: Key Information option should not be clickable.
[6 empty] | Actual Result: key Information Option Is clickable . when click on that No action perform. | wrong Functional | Testing | Done | Low |  | Neha | 2023-01-05 | Akash | 2023-01-06
2023-01-05 | D_kokanSearch_Home | kokanSearch | Home | Tours | Direction of the arrows shows wrong. | Steps: 1.Click o tours
2.Click Go to Details itinerary
3.Click on Arrow
Expected Result: Arrow Direction should be Downword when user open details
[6 empty] | Actual Result: Direction of the arrows shows wrong. Arrow shows Upword direcrtion. | wrong Functional | Testing | Done | Low |  | Neha | 2023-01-05 | Akash | 2023-01-06
2023-01-05 | D_kokanSearch_Home | kokanSearch | Home | Place |  | Steps: 1.Click onPlace on Home PAge
Expected Result: When Mouse Over On 'Category Option ' coursor should be changed
[6 empty] | Actual Result: Mouse cursor not changes. | Wrong Functional | Testing | Done | Low |  | Neha | 2023-01-05 | Akash | 2023-01-06
2023-01-05 | D_kokanSearch_Home | kokanSearch | Home | Village | Without selectingmandatory field click on submit button displyed message"Name Error". | Steps: 1.Click on Village on home page
2.Form displayd
3.Click on Submit button
Expected resut: Without filled form and click on submit button displayed error note." Please select this field'
[6 empty] | Actual Result: Withot selectingmandatory field click on submit button displyed message"Name Error". | Wrong Functional | Testing | Done | Medium |  | Neha | 2023-01-05 | Akash | 2023-01-06
2023-01-05 | D_kokanSearch_Home | kokanSearch | Home | Village | dispalyed error message " Does not exist at village" | Steps: 1.Click on Village
2.Select District
3.Select Taluka
4.Click on Sabmit button
Expected Result : Without selected Village click on submit button , displayed error note" Please select village".
[6 empty] | Actual Result:Withing selecting Village click on Submit button dispalyed error" Does not exist at village" | Wrong Functional | Testing | Done | Medium |  | Neha | 2023-01-05 | Akash | 2023-01-06
2023-01-05 | D_kokanSearch_Home | kokanSearch | Home | Sliders | No any action perform | Steps: 1.Go to home page
2.Home page Slider
3.Click on View More option
Expected Result: Click on 'View more' details page should be displayed
[6 empty] | Actual reult: No any action perform . page is refresh onnly. Detail page not display. | Missing defect | Testing | Done | Medium |  | Neha | 2023-01-05 | Akash | 2023-01-06
2023-01-05 | D_kokanSearch_Home | kokanSearch | Home | Siders | Share' button is not displying properly. | Steps: 1.Click on Home
2.Click on Busines Slider
3.Go to details page
Expected Result: In Business Details page 'Share' button should be displayed at Top right corner
[6 empty] | Actual result: 'Share' button is not displying properly. | Missing defect | Testing | Done | Medium |  | Neha | 2023-01-05 | Akash | 2023-01-06
2023-01-05 | D_kokanSearch_Home | kokanSearch | Search Bar |  | Clear button is missing. | Steps: 1. Enter Data in search bar
Expected Result: If user clear the Entered data , Clear butoon should be visible.
[6 empty] | Actual Result: Clear button is missing. | Missing defect | Testing | Open | Medium |  | Neha | 2023-01-05 | Akash
2023-01-05 | D_kokanSearch_Home | kokanSearch | Search Bar |  | Click on that displayed error message"Page not found" | Steps: 1.Enter Data in to search bar
2.Click on Suggested card image
Expected RSeult: Page should be redirect to result page.
[6 empty] | Actual Result: Click on that displayed error message"Page not found" | Wrong Fuctional | Testing | Done | Medium |  | Neha | 2023-01-05 | Akash | 2023-01-06
2023-01-06 | D_kokanSearch_Home | kokanSearch | Search Bar | List page | Read more button colour displed same as Text colour | Steps: 1.View Search List page
2.Click on one Result
3.View Detail page
Expected Result: In About us ,' Read more 'button dispayled Properly
[6 empty] | Actual result: Read more button colour displed same as Text colour | Non functional | Testing | Done | Not a bug |  | Neha | 2023-01-06 | Akash | 2023-01-06
2023-01-06 | D_kokanSearch | kokanSearch | search | Business list page | Concact number is not clickable. | Steps: 1.Click On any Business
2. View Details
Expected Result Mouse over on Contact Number, it should be clickable
[6 empty] | Actual result: Concact number is not clickable. | Non functional | Testing | Done | Low |  | Neha | 2023-01-06 | Akash | 2023-01-06
2023-01-07 | D_kokanSearch | kokanSearch | Home | Slider | dispalyed message 'Page not found'. | Steps: 1.Click on Tourist Palce
Expected Result: Click o nTourist Place ,detals details page should be open.
[6 empty] | Actual REsult: dispalyed message 'Page not found'. | Wrong Functional | Testing | Done | Medium |  | Neha | 2023-01-07 | Akash | 2023-01-08
2023-01-07 | D_kokanSearch | Kokan search | Home | Slider |  | Steps; 1.Go to Slider
2.Click on View More in Tourist Palce
Expected Result: Click on View more ,details page should be displayed.
[6 empty] | Actual REsult: Dispayed error message "Page nort found" | Wrong functional | Testing | Done | Medium |  | Neha | 2023-01-07 | Akash | 2023-01-08
2023-01-07 | D_kokanSearch | Kokan search | Home | Profile | Cursor not chaanging | steps: 1.Click on Profile
2.Click on Change Password
Expected Result: When Mouse Over on 'change proofile' cousor should be change.
[6 empty] | Actual Result: Cursor not chaanging . | Wrong functional | Testing | Done | Medium |  | Neha | 2023-01-07 | Akash | 2023-01-08
2023-01-07 | D_kokanSearch | Kokan search | Village Government Info | Government Info | Mobile Number Field' is accepted Alphanumeric vlaues. | Steps: 1.Click on Village
2. Gov Information
3. Enter Mobile number
Expected result: 'Mobile number' field should be accepted 10 digit numbers only.
[6 empty] | Actual Result: 'Mobile Number Field' is accepted Alphanumeric vlaues. | Wrong functional | Testing | Done | Medium |  | Neha | 2023-01-07 | Akash | 2023-01-08
2023-01-07 | D_kokanSearch | Kokan search | Village | Government Info | Mobile Number ' filed is accepting less than 10 digit or more than 10 digit numbers. | Steps: 1.Click on Village
2. Gov Information 3.Click on Grampanchayat info
Expected Result: 'Mobile Number' field should not be accepted less and more than 10 digit numeric value.
[6 empty] | Actual Result: 'Mobile Number ' filed is accepting less than 10 digit or more than 10 digit numbers. | Wrong functional | Testing | Done | Medium |  | Neha | 2023-01-07 | Akash | 2023-01-08
2023-01-07 | D_kokanSearch | Kokan search | Village | Government Info | In 'Address' field Scripting language is accepted | Steps: 1.Click on Village
2.Click on
3. Gov Information
4.Click on Police Station 5.Enter Address
Expected Result: In 'Address ' field Scripting values should not be accepted.
[6 empty] | Actual Result: In 'Address' field Scripting language is accepted | Wrong functional | Testing | Done | Medium |  | Neha | 2023-01-07 | Akash | 2023-01-08
2023-01-07 | D_kokanSearch | Kokan search | Village | Government Info | Field accepting alphanumeric values | Steps: 1.Click on Village
2.Click on
3. Gov Information
4. Social Work 5. Social worker number
Expected Result: In 'Social worker number' field should be accepted 10 digit numeric value.
[6 empty] | Actual result: In 'Social Worker number' filed is accepting alphanumeric values. | Wrong functional | Testing | Done | Medium |  | Neha | 2023-01-07 | Akash | 2023-01-08
2023-01-07 | D_kokanSearch | Kokan search | Village | Government Info | Filed is accepting less than or more than 10 digit alphanumeric valuyes. | Steps: 1.Click on Village
2.Click on
3. Gov Information
4. Social Work 5. Social worker number
Expected Result: In 'Social worker number' field should be accepted 10 digit numeric value.
[6 empty] | Actual result: In 'Social worker number' field is accepted less than 10 or more than 10 digit alphanumeric values | Wrong functional | Testing | Done | Medium |  | Neha | 2023-01-07 | Akash | 2023-01-08
2023-01-07 | D_kokanSearch | Kokan search | Village | Government Info | Dispalying 'Please select an item' | Steps: 1.Click on District
2. Select taluka
3. Click on Submit Button
Expected Result: It should Dispalyed "Please select Taluka"
[6 empty] | Actual Result: Dispalying note 'Please select an item' | Non functional | Testing | Done | Not a bug |  | Neha | 2023-01-07 | Akash
2023-01-07 | D_kokanSearch | Kokan search | Village |  | Displaying note 'Please select an item'. | Steps: 1.Click on District
2.Select taluka
3.Click on submit button
Expected Return: Dispalyed" Please select Village".
[6 empty] | Actual Return: Displaying note 'Please select an item'. | Non functional | Testing | Done | Not a bug |  | Neha | 2023-01-07 | Akash
2023-01-07 | D_kokanSearch | Kokan search | Village | Cluture | Field accepting Alphanumeric values. | Steps: 1.Click pn Culture
2.Fill the Festival form
3.Click on Bhajan....
4.Enter Name
5.Enter Number
Expected result: In Number field' It should be Accepted only numeric value'.
[6 empty] | Actual Result: In number field' It accepting Alphanumeric values. | wrong functional | Testing | Open | Medium |  | Neha | 2023-01-07 | Akash | 2023-01-08
2023-01-09 | D_kokanSearch | Kokan search | Village | Cluture | Field accepting Alphanumeric values. | Steps: 1.Click pn Culture
2.Fill the Festival form
3.Click on Bhajan.... 4.Click on add Button
5.Enter Name
6.Enter Number 7.Click on save
Expected result: In Number field' It should be Accepted only numeric value'.
[6 empty] | Actual Result: In number field' It accepting Alphanumeric values. | wrong functional | Testing | Open | Medium |  | Neha | 2023-01-09 | Akash | 2023-01-10
2023-01-09 | D_kokanSearch | Kokan search | Village | Cluture | Field accepting Alphanumeric values. | Steps: 1.Click pn Culture
2.Fill the Festivall form
4.Click on add Button
5.Enter Name
6.Enter Number 7.Click on save
Expected result: In All forms the Number field' should be Accepted only numeric value'.
[6 empty] | Actual Result: In number field' It accepting Alphanumeric values. | wrong functional | Testing | Open | Medium |  | Neha | 2023-01-09 | Akash | 2023-01-10
2023-01-10 | D_kokanSearch | Kokan search | Village | Cluture | Background image not dispalying Properly. | Steps: 1.View Home page
Expected Result: Background imge slider should be dispalyed Properly.
[6 empty] | Actual Result: Background image not dispalying Properly. | wrong functional | Testing | Open | Medium |  | Neha | 2023-01-10 | Akash | 2023-01-10
2023-01-10 | D_kokanSearch | Kokan search | Village | Emergency Number in village | Phone number 'field is accepting alphanumeric values. | Steps: 1.Click on Add village
2.Click on Emergency number in village
3.Phone number filed
Expected Number: "phone number 'field should be accepted Numeric values '.
[6 empty] | Actual Number: "Phone number 'field is accepting alphanumeric values. | wrong functional | Testing | Open | Medium |  | Neha | 2023-01-10 | Akash | 2023-01-10
2023-01-10 | D_kokanSearch | Kokan search | Village | Edit Village |  | Steps: 1.Click on Village
2.Click on Edit Village
Expected Result: "Phone number "field should be accepted Numeric values.
[6 empty] | Actual Rwesult: Edit Form "Phone number field is accepting Alphanumeric values". | wrong functional | Testing | Open | Medium |  | Neha | 2023-01-10 | Akash | 2023-01-10
2023-01-10 | D_kokanSearch | Kokan search | Village | Edit Village | heading is missing' | Steps: 1.Click on Village
2.Clickon Edit
3.CLick on VIew Village Photo
Expected Result: When click in on Village Heading should be idispalyed "Village Photo
[6 empty] | Actual Result: 'heading is missing' | Misssing Defect | Testing | Open | Low |  | Neha | 2023-01-10 | Akash | 2023-01-10
2023-01-11 | D_kokanSearch | Kokan search | Viillage | Edit Village | When Click on Submit button no any pop message showing | Steps: 1.Click on Edit Village
2.Edit Form
3.Click on Submit Button
Expected result: Click on Submited Button ,displayed Message ' Form Upadate Successfully".
[6 empty] | Actual Result: When Click on Submit button no any pop message showing | Missing Defect | Testing | Open | Low |  | Neha | 2023-01-11 | Akash
2023-01-11 | D_kokanSearch | Kokan search | Viillage | Edit Village | Number Field is Accpeted Alphanumeric Values. | Steps: 1.Click on edit village
2.Click on Cluture
3.Click on Plus Button
4.Filled Number field
Expected Result: NUmber Filed should be accepted Numeric Values only.
[6 empty] | Actual Result: Number Field is Accpeted Alphanumeric Values. | wrong functional | Testing | Open | Medium |  | Neha | 2023-01-11 | Akash
2023-01-11 | D_kokanSearch | Kokan search | Viillage | Edit Village | Numerber Field is accepted Less than 10 or More than 10 digit valus | Steps: 1.Click on edit village
2.Click on Cluture
3.Click on Plus Button
4.Filled Number field
Expected Result: NUmber Filed should be accepted 10 digit Numeric Values only.
[6 empty] | Actual Result: Numerber Field is accepted Less than 10 or More than 10 digit valus | wrong functional | Testing | Open | Medium |  | Neha | 2023-01-11 | Akash
2023-01-11 | D_kokanSearch | Kokan search | Viillage | Edit Village./ADD | Numerber Field is accepted Less than 10 or More than 10 digit valus | Steps: 1.Click on edit village/Add
2.Click on Bank
3.Click on Plus Button
4.Filled Number field
Expected Result: NUmber Filed should be accepted 10 digit Numeric Values only.
[6 empty] | Actual Result: Numerber Field is accepted Less than 10 or More than 10 digit valus | wrong functional | Testing | Open | Medium |  | Neha | 2023-01-11 | Akash
2023-01-11 | D_kokanSearch | Kokan search | Viillage | Edit Village/Add | Numerber Field is accepted Less than 10 or More than 10 digit valus | Steps: 1.Click on edit village/Add
2.Click on Bank
3.Click on Plus Button
4.Filled Number field
Expected Result: NUmber Filed should be accepted 10 digit Numeric Values only.
[6 empty] | Actual Result: Numerber Field is accepted Less than 10 or More than 10 digit valus | wrong functional | Testing | Open | Medium |  | Neha | 2023-01-11 | Akash
2023-01-11 | D_kokanSearch | Kokan search | Viillage | Edit Village | Field is accepting Alphanumeric values | Steps: 1.Click on edit village/Add
2.Click On ATM
3.Enter ATM name
EXpected Result: Field should be accepted Alphabets only.
[6 empty] | Actual Result: Field is accepting Alphanumeric values | wrong functional | Testing | Open | Medium |  | Neha | 2023-01-11 | Akash
2023-01-11 | D_kokanSearch | Kokan search | Viillage | Edit Village | Field is accepting Scripting language | Steps: 1.Click on edit village/Add
2.Click On ATM
3.Enter ATM name
4.Enter ATM address
Expected Result: Field should be accepted Alphanumeric VAlues.
[6 empty] | Actual Result: Field is accepting Scripting language | wrong functional | Testing | Open | Medium |  | Neha | 2023-01-11 | Akash
2023-01-11 | D_kokanSearch | Kokan search | Viillage | Edit Village | Numerber Field is accepted Less than 10 or More than 10 digit valus | Steps: 1.Click on Edit Village
2.Click on Organization
3.Filled form
4.Click Plus Button
Expected Result: NUmber Filed should be accepted 10 digit Numeric Values only.
[6 empty] | Actual Result: Numerber Field is accepted Less than 10 or More than 10 digit valus | wrong functional | Testing | Open | Medium |  | Neha | 2023-01-11 | Akash
2023-01-11 | D_kokanSearch | Kokan search | Viillage | Edit Village | Number Field is Accpeted Alphanumeric Values. | Steps: 1.Click on Edit Village
2.Click on Organization
3.Filled form
4.Click Plus Button
Expected Result: NUmber Filed should be accepted Numeric Values only.
[6 empty] | Actual Result: Number Field is Accpeted Alphanumeric Values. | wrong functional | Testing | Open | Medium |  | Neha | 2023-01-11 | Akash
2023-01-11 | D_kokanSearch | Kokan search | Viillage | Edit Village | Numerber Field is accepted Less than 10 or More than 10 digit valus | Steps: 1.Click on Edit Village
2.Click on Additional Information
3.Click on Plus sign
4.Enter Respectable Person Name
5.Enter MObile number
Expected Result: NUmber Filed should be accepted 10 digit Numeric Values only.
[6 empty] | Actual Result: Numerber Field is accepted Less than 10 or More than 10 digit valus | wrong functional | Testing | Open | Medium |  | Neha | 2023-01-11 | Akash
2023-01-11 | D_kokanSearch | Kokan search | Viillage | Edit Village | Number Field is accepted Less than 10 or More than 10 digit valus | Steps: 1.Click on Edit Village
2.Click on Additional Information
3.Click on Plus sign
4.Enter Respectable Person Name
5.Enter MObile number
Expected Result: NUmber Filed should be accepted 10 digit Numeric Values only.
[6 empty] | Actual Result: Numerber Field is accepted Less than 10 or More than 10 digit valus | wrong functional | Testing | Open | Medium |  | Neha | 2023-01-11 | Akash
2023-01-11 | D_kokanSearch | Kokan search | Viillage | Edit Village | Respectable Person name' field is accepting alphanumeric value. | Steps: 1.Click on Edit Village
2.Click on Additional Information
3.Click on Plus sign
4.Enter Respectable Person Name
Expected Result: 'Respectable Person Name ' field should be accepted Alphanumeric value.
[6 empty] | Actual Result: 'Respectable Person name' field is accepting alphanumeric value. | wrong functional | Testing | Open | Medium |  | Neha | 2023-01-11 | Akash
Pending
2023-01-12 | D_kokanSearch | Kokan search | Viillage |  |  | Steps: 1.Click on Edit Village
2.Click on Village photo
2023-01-31 | D_kokanSearch | Kokan search | Viillage | Edit Village | Add more than Two Plus button click on save button showing error message"Somtiong went wrong | Steps: 1.Click on Edit Village
2.Enter About Information
3.Enter Grampanchayt Information
4.Click on plus button 5.Enter Information
5.Click on Save
|  |  |  | Note: Same in atm,Connectivity,organisation,Additional Info |  | Expected Result: Add more than two (+)button Entered inforamtion after Click on save dispalyed message "Data send for approval"
[6 empty] | Actual Result: Add more than Two Plus button click on save button showing error message"Somtiong went wrong | wrong functional | Testing | Open | Medium |  | Neha | 2023-01-31 | Akash

## WEB1
|  | Red color |  | Critical Severity |  |  | Close Defect
|  | Yellow color |  | High Severity |  |  | Reopen Defect
|  | Orange color |  | Medium Severity |  |  | Not a defect
|  | Green Color |  | Low severity |  |  | Open
DATE | DEFECT_ID | PROJECT NAME | MODULE NAME | SUB-MODULE NAME | SUMMARY | DESCRIPTION | DEFECT TYPE | PHASE | STATUS | SEVERITY | PRIORITY | REPORTED BY | REPORTED ON | ASSIGN TO | Defect Resolved date
2023-03-24 | D_Add Event_1.0 | Kokan Search | Add Event |  | Without Youtube and Facebook link Form not submited | Steps: 1.Click on Add Event
2.Enter Event NAme
3.Enter Start date
4.Enter End date
5.Filled Manadatory Filed
6.Click on Submit
Expected Result: Without Entered Youtube link and Facebook link click on submit button form should be submited.
[6 empty] | Actual Result: Without Youtube and Facebook link Form not submited Manadatory (*) mark is missing. | Functional Defect | Testing | Open | Medium |  | Neha | 2023-03-24 | Akash
2023-03-24 | D_Add event1.2 | Kokan Search | Add Event | Event Details |  | Steps: Click onadded Event
2.Go to Event Detail page
2. Click on View button
Expectd Result: Added "Youttube "should be dispalyed in Event Details page
[6 empty] | Actual Result: "Youtube link" is not displayed | Wrong Functional | Testing | Open | Medium |  | Neha | 2023-03-24 | Akash
2023-03-24 | D_Add event1.3 | Kokan Search | Add Event | Event Details |  | Steps: 1.Click on Added Event
2.Go to Event Detail page
3. Click on View button
Expected Result: Click on "Face book" link Page should be redirect to next page
[6 empty] | Actual result:Click on Added" Face book" link dispalying messgae "Page not Found" | Wrong Functional | Testing | Open | Medium |  | Neha | 2023-03-24 | Akash
2023-03-24 | D_Upload Album2.0 | Kokan Search | Upload album |  | Added album is dispalyimng without admin approve | Steps: 1.Click on Upload Photo
2.Enter Album name
3.album Category
4. Select Location
5.Select Cover photo
6.Click on Submit button
Expected Result: Without admin Approval Added Album should not be Displayed in Album List.
[6 empty] | Actual Result: Added album is dispalyimng without admin approve | Wrong Functional | Testing | Open | Medium |  | Neha | 2023-03-24 | Akash
2023-03-24 | D_Add Business3.0 | Kokan Search | Add Business |  | Feature date is seleting in DOB field | Steps: 1.Click on add Business
2.Observe Business form
3.Filled mandatory fied
4.Enter DOB
Expected Result: Feature date should not be selecte in "DOB" field
[6 empty] | Actual Result: Feature date is seleting in DOB field | Wrong Functional | Testing | Open | Medium |  | Neha | 2023-03-24 | Akash

## Admin
|  | Red color |  | Critical Severity |  |  | Close Defect
|  | Yellow color |  | High Severity |  |  | Reopen Defect
|  | Orange color |  | Medium Severity |  |  | Not a defect
|  | Green Color |  | Low severity |  |  | Open
DATE | DEFECT_ID | PROJECT NAME | MODULE NAME | SUB-MODULE NAME | SUMMARY | DESCRIPTION | DEFECT TYPE | PHASE | STATUS | SEVERITY | PRIORITY | REPORTED BY | REPORTED ON | ASSIGN TO | Defect Resolved date
2023-03-26 | D_Tourist Place 1.0 | Kokan Search | Tourist Place |  | "Entered Marathi description " is not displaying | Steps: 1.Click on Tourist Place
2.Click on Add Tutist place
3.Select Touridt type
4.Enter Tourist place name
5.Enter Description 6.Click on Save
Expected Result: In description field ,"Enterd Description should be displapyed properly
[6 empty] | Actual Result: "Entered Marathi description " is not displaying ??? is dispaying at descriptin field | Wrong functional | Testing | Open | Medium |  | Neha | 2023-03-26 | Akash
2023-03-26 | D_Tourist Place 1.1 | Kokan Search | Tourist Place |  |  | Stes: 1.Click on Tourist Palce
2.List of the Tourist place
Expected Result: All Heading s should be dispalyed in Same colour
[6 empty] | Actual Result: "Tourist Place Information" Heading displaying in Black colour | Non Functional | Testing | Open | Low |  | Neha | 2023-03-26 | Akash
2023-03-26 | D_Add Business 1.1 | Kokan Search | Add Business |  | Scripting Language is accepting in "Address" filed | Steps: 1.Enter Full name
2.Enter Mail id
3.Enter Mobile number
4.Enter Address 1
5.Enter address 2
Expected Result: Scripting language should not be accepted in Address filed
[6 empty] | Actual Result: Scripting Language is accepting in "Address" filed. | Wrong functional | Testing | Open | Medium |  | Neha | 2023-03-26 | Akash

## App
| Red color |  | Critical Severity |  |  | Close Defect
| Yellow color |  | High Severity |  |  | Reopen Defect
| Orange color |  | Medium Severity |  |  | Not a defect
| Green Color |  | Low severity |  |  | Open
DATE | PROJECT NAME | MODULE NAME | SUB-MODULE NAME | SUMMARY | DESCRIPTION | DEFECT TYPE | PHASE | STATUS | SEVERITY | PRIORITY | REPORTED BY | REPORTED ON | ASSIGN TO | Defect Resolved date
2023-01-04 | Kokansearch | Home Page |  | Nav Bar is not dispalying | Steps:
1.Go to Home page
Expected Result: Nav Bar dispalying properly on Home page
[5 empty] | Actual Result: Nav Bar not dispalying on home page of the Mini Tab | missing defect | open | Testing | High |  | Neha | 2023-01-04 | Akash | 2023-01-08
2023-01-04 | Kokansearch | Home Page |  | Back slider is not scrolling at same time | Step: 1.Go to Home Page
Expected Result: Back Slider should be scrolling properly in device
[5 empty] | Actual result: Back slider is not scrolling at time. Resolution time is not same | Wrong Defect | open | Testing | Medium |  | Neha | 2023-01-04 | Akash | 2023-01-08
2023-01-04 | Kokansearch | Home Page |  | Alignment not displaying properly | Step: 1.Go to Home Page
Expected Result: Slider alignment should be dipslayed properly
[5 empty] | Actual result: Alignment not displaying properly on Tab | Wrong Defect | open | Testing | Medium |  | Neha | 2023-01-04 | Akash | 2023-01-08
2023-01-05 | Kokansearch | Home Page | Slider | Slider Image displaying rectangular in shape | Steps: 1. Go to Home page
Expected Result: Same size of images should be dispalyed in all device
[5 empty] | Actual Result: Slider Image displaying in rectangular shape in Tab | Wrong Defect | open | Testing | Medium |  | Neha | 2023-01-04 | Akash | 2023-01-08
2023-01-05 | Kokansearch | Home Page | Slider | Arrow shows upword side in android | Steps: 1.Click in Album slider image
2.CLick on images
3.Scroll images
Expecteed result: Scrolled arrow should be dispalyed middle of the card
[5 empty] | Arrow shows upword side in android | non fuctional | open | Testing | low |  | Neha | 2023-01-04 | Akash | 2023-01-09
2023-01-05 | Kokansearch | Home Page | Slider | In Album card size not showing properly in Tab. | Steps" 1.Click on Menu
2.Click on album
Expected Result: Added album should be dispalyed Properly.
[5 empty] | Actual Result: In Album card size not showing properly in Tab. | Wrong functional | open | Testing | Low |  | Neha | 2023-01-04 | Akash | 2023-01-09
2023-01-06 | Kokansearch | Home Page | Slider | Image and Content looks much closer. | Steps: 1.Click on Business Card
2.View Business detail page
Expecter Result: Details page should be dispalyed Properly.
[5 empty] | Actual Result: Image and Content looks much closer. | Non functional | Open | Testing | Low |  | Neha | 2023-01-06 | Akash | 2023-01-09
2023-01-06 | Kokansearch | Home Page | Apps | Model is Not Displaying Properly in Mobile view | Steps 1.Click on Model
[5 empty] | Actual Result: After Click on Model its open away from the menu Button. | Non functional | Open | Testing | Low |  | Neha | 2023-01-06 | Akash | 2023-01-08
2023-01-06 | Kokansearch | Home Page | Apps | Album Card alignment not showing properly. | Steps: 1.Click on Model
2.Click on Upload photo
[5 empty] | Actual Result: Album Card alignment not showing properly in Tab | Wrong Functional | Open | Testing | Medium |  | Neha | 2023-01-06 | Akash | 2023-01-09
2023-01-06 | Kokansearch | Upload Photo | Apps | Share button on the card is displaying below the album Image. | 1.Click on Model
2.Click on Upload Photo
[5 empty] | Actual Result: Share button on the card is displaying below the album Image. | Wrong functional | Open | Testing | Medium |  | Neha | 2023-01-06 | Akash | 2023-01-09
2023-01-06 | Kokansearch | Upload Photo | Apps | Sticky bar not visible in Tab After Scroll down. | 1.Click on Model
2.CLick on Upolad Photo
[5 empty] | Actual Result: Sticky bar not visible in Tab After Scroll down. | Non functional | Open | Testing | Medium |  | Neha | 2023-01-06 | Akash | 2023-01-09
2023-01-06 | Kokansearch | Upload Photo | Apps | content shows out of the card. | 1.Click on Model
2.Click on Upload
3.View My Album
[5 empty] | Actual Result: Tha content on the card is not dispalting properly. content shows out of the card in Tab | Non functional | Open | Testing | Medium |  | Neha | 2023-01-06 | Akash | 2023-01-09
2023-01-06 | Kokansearch | Event Calander | Apps | Not properly scroll down | Steps: 1.Click on Event calender
[5 empty] | Actual Result: When Event Page scroll down it's not dispalying properly . | Non functional | Open | Testing | Medium |  | Neha | 2023-01-06 | Akash | 2023-01-09
2023-01-06 | Kokansearch | My Profile | Apps | Profile page card size dispalying large in Tab | Steps: 1.Click on My Profile
2.Click Edit My profile
3.Click on submit
[5 empty] | Actual Result: Profile page card size dispalying large in Tab | Non functional | Open | Testing | Medium |  | Neha | 2023-01-06 | Akash | 2023-01-09
2023-01-06 | Kokansearch | Home | Village |  | Steps: 1. Home Page
2.Click on Village
3.Filled the form
4.Click on Submit button
5.Click on 'Click here to add information;
Expected Result: Added Content shoud be dispalyed on Side Bar.
[5 empty] | Actual Result: Villages Forms name shows out of the side bar. | Wrong Functional | Testing | Open | Medium |  | Neha | 2023-01-06 | Akash | 2023-01-09
2023-01-06 | Kokansearch | Home | Village | Detailed itinerary' heading is closer to the imges | Steps:
1.Click on Tours
2.Click on Listing page
Expected Result: All details should be dispalyed properly Alignment should be displayed properly
[5 empty] | Actual Result: 'Detailed itinerary' heading is closer to the imges | Non Functional | Testing | Open | Not a bug |  | Neha | 2023-01-06 | Akash | 2023-01-09
2023-01-10 | Kokansearch | Business form |  | PAge name' are not showing. | Steps: 1.Click on Add business
Expectd Result: In business form' page name ' should be dispalyed
[5 empty] | Actual Result: "PAge name' are not showing. (user info, business info..) | Missing | Testing | Open | Low |  | Neha | 2023-01-06 | Akash | 2023-01-10
2023-01-10 | D_kokanSearch | Kokan search | Village | Edit Village | Not showing properly. | Steops: 1.Click on Village
2.CLick on Edit form
Expected Result: "Submit " button should be dispalyed properly in all form
Actual Result:
[6 empty] | "Submit " button is mix within Adds. Not showing properly. | Non functioanl | Testing | Open | Low |  | Neha | 2023-01-10 | Akash